## weights_volumes
[7 empty] | total weight (lbs) | total volume (cu feet) | weight to ship in June 2023 | 2023 part entered into SIP? |  | aluminium poles (2 m) | weight of aluminium | bamboos | weight of bamboos | pvc piping (3m) | wood slats (1m)
Instrument | Number of sites | Total person-days each season | Team member responsible | Notes on deployment | Notes on acquiring instrumentation | Power system | [5 empty] | 3.36 |  | 0.42
dGNSS | 8 | 7 | Stevens | Installed on aluminum glacio poles along a center line and around a lake | To be borrowed from UNAVCO (see letter) | Supplied by UNAVCO | 640 | 80 | 192 | yes |  | 0 | 0 | 0 | 0 | 0 | 0
ApRES | 2 overwinter locations + 2 repeated surveys in each season) | 4 | Porter | Buried and designed to run for nearly the full 16 months | To be purchased from BAS (see quote) | UNAVCO have designed and will supply a new ApRES power system | 263 | 23.4167 | 75 | yes |  | 12 | 40.32 | 4 | 1.68 | 4 | 12
UAV | Two surveys, repeated twice daily over limited period | 7 | Davison | Can be deployed from camp or a temporary base closer to the surveys, range ~60km) | To be purchased and constructed (budget estimated from Chudley et al. (2019)) | Self-contained, on board electrical power system. | 370 | 27.5394 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Passive seismometers | 3 | 2 | Davison | Installed in short post-holes drilled with the hand auger (see below) in the bottom of ~2 m pits. | To be borrowed from PASSCAL (see letter) | Designed by PASSCAL to use a combination of lithium-ion and lead-acid batteries to minimize weight | 1300 | 44 | 240 | yes |  | 4 | 13.44 | 2 | 0.84 | 0 | 0
AWS | 2 | 2 | Porter | Main mast extension will be installed in 4 m borehole and secured with buried guylines | To be purchased from Campbell Scientific Inc. (see quote). | Solar panels and battery bank | [6 empty] | 0 |  | 0
Thermistor strings | 2 | 2 | Porter | Requires installation in 10 m boreholes. Data will be logged on the AWS logger. | Strings to be purchased from GEOKON PTE LTD (see quote), hand auger to be borrowed from US IDP (see letter). | Powered by AWS power system | 25 | 4 | 0 |  |  | 0 | 0 | 4 | 1.68 | 0 | 0
Hand auger for thermistor strings | [6 empty] | 113 | 7.5 | 113 | [5 empty] | 0
aluminium poles | [14 empty] | 0
extra equipment (laptops, spare cables, tools) | [6 empty] | 60 | 10 | 0 | [5 empty] | 0
honda generator 2kw *2 | [6 empty] | 100 | 24 | 0 | [5 empty] | 0
misc bamboos | [13 empty] | 10 | 4.2
[6 empty] | total | 2871 | 220.456 | 620 | 0 | 0 | 19.36 | 53.76 | 20.42 | 8.4 | 4 | 12
cubic inches per cubic feet
1728
Note on M1: 0.42 lbs per foot: https://www.onlinemetals.com/en/buy/aluminum/1-od-x-0-125-wall-x-0-75-id-aluminum-round-tube-6063-t52-extruded/pid/21001 -Jonathan Kingslake
Note on O1: 1/2 /1in Dia. x 6ft High Weight: 0.7 lbs https://www.jamaligarden.com/1-1-1-2-and-2-inch-dia-natural-bamboo-stakes.html -Jonathan Kingslake
Note on Q1: just added some weight to the aluminium poles for the SIP -Jonathan Kingslake
Note on R1: assumed 3lbs each for SIP -Jonathan Kingslake
Note on H3: I have emailed UNAVCO to ak about weights. -Jonathan Kingslake Joe Pettit says they are 80lbs each, -Jonathan Kingslake
Note on I3: guess, based on seismometer volumes -Jonathan Kingslake
Note on J3: based on Mar 21 2023 email to Joe Pettit -Jonathan Kingslake
Note on M3: included in weights we got from UNAVCO -Jonathan Kingslake
Note on H4: calculated based on 3 units -Jonathan Kingslake
Note on M4: conservatively 6 per ApRES site -Jonathan Kingslake
Note on Q4: 2 per site -Jonathan Kingslake
Note on H5: emailed black swift technologies -Jonathan Kingslake details here and the volume from Mar 14 2023 email 'potential S2 purchase' -Jonathan Kingslake
Note on H6: Centaur and Trillium Compact from Mar 20th email -Jonathan Kingslake
Note on I6: from Mar 20 2023 email -Jonathan Kingslake
Note on H7: emailed Dave to put me in contact with Inmountain Environmental - the company we have a quote from for the AWS. -Jonathan Kingslake I had a conversation with them and they would like to know more details about what we want to measure. -Jonathan Kingslake They are getting back to me with weights and (i think) volumes -Jonathan Kingslake
Note on H8: emailed GEOKON - the company we have a quote for the thermistor strings. -Jonathan Kingslake they said 25lbs, so I will make 35lbs with the case -Jonathan Kingslake

## aws
original quote
radiation sensors
2* wind sensors for contingency
barometer
sonic ranger
iridium system
10ft Tower w/Base, Adjustable Mast, & Grounding Kit
temo and rh sensor

## thermistors
0 | 0
0.25 | 0.5
0.5 | 1
0.75 | 1.5
1 | 2
1.25 | 2.5
1.5 | 3
1.75 | 3.5
2 | 4
2.5 | 4.5
3 | 5
3.5 | 5.5
4 | 6
4.5 | 6.5
5 | 7
5.5 | 7.5
6 | 7.75
6.5 | 8
7 | 8.25
7.5 | 8.5
8 | 8.75
8.5 | 9
9 | 9.25
9.5 | 9.5

## apres
This info comes from the proforma forms from Elizabeth stored in /Users/jkingslake/Documents/projects/current_projects/AntPen_NSF_NERC/AntPen_NSF_NERC/shipping_weights/apres
| weight (lbs) | volume (cubic feet)
2 ss antennas | 33 | 2.25
6 bowtie antennas | 40 | 6.3333
3 ApRES | 40 | 9.5833
batteries (36Ah * 3) | 75 | 3
solar panels + solar controllers | 75 | 2.25
cubic inches per cubic feet
1728
Note on B7: estimated -Jonathan Kingslake